--Management Plan
Stella Greenvoss, David Haddad, Anna Norris, Garrett Caldwell

- Team Organization:

While everyone codes, Stella is the lead architect for the database schema, Anna is responsible for quality assurance, Garrett is taking the lead on documentation and UI development, and David is responsible for algorithm stability and determinism.

  - Team Roles:

    - Team Leader: David Haddad

    - Team Communicator: Stella Greenvoss

    - Project Master & QA Lead: Anna Norris

    - Project Delivery and Documentation Lead: Garrett Caldwell

  - Scrum Roles:

    - Scrum Master: Anna Norris

    - Project Owners: due to the nature of this project, we all function as project owners, as well as including several friends who indicated a tool like a social schedular that reduces friction was a user desire.

      - Working iterative versions will be presented to at least one individual outside the group for feedback before continuing the next sprint planning session.

    - Development Team: we are all part of the development team as group development is crucial for this course

- Work division:

  - Coding: All members are required to complete a comparable process on the actual coding and development part of the project.

  - Team Management: Team Leader is the point person on ensuring the team dynamic is working and communication is occurring, but all members are required to play a role in the team dynamic.

- Decision-making:

  - Democratically decide on features and next steps

  - While we strive for group consensus. In the event of a tie, the Team Member assigned as “Owner” of that specific module/requirement/task will have the final say on the technical implementation details.

- Communication:

  - We will meet in person at least three times a week.

  - We’ll hold a longer meeting on Tuesday for sprint planning and retrospective.

  - Meet 15 minutes on other four weekdays online or in person (daily scrum).

- Work breakdown schedule:

  - Week 1

    - Schedule Weekly Group Meeting and Scrums – All Members

    - Project Idea and Plan – All Members

  - Week 2

    - SRS development (first steps, structural draft with AI assistance) – David

  - Week 3

    - In Class Presentation – All Members

    - SDS, SRS, and Management Plan Submission – All Members

      - SDS Development – Anna

      - SRS Finalization – All members (Stella Lead)

      - Management plan -- Garrett

  - Week 4

    - Establish server-client communication – Anna

    - Create a working homepage – Garrett

    - Basic Busy/Free computation algorithm – David

    - Establish and normalize event storage and database structure - Stella

    - Milestone: Progress Meeting – All Members

  - Week 5

    - Google OAuth and Login Modules Finalized – David & Stella

    - Connect Google Calendar (integration) – Anna

    - Basic UI displays availability to demonstrate algorithm stability – Garrett

    - Group Invitation Implementation – Garrett & Anna

  - Week 6

    - Milestone: Progress Meeting 2 – All Members

    - Database Stores Event Information Securely – Stella

    - Display Calendar Flat (not editable) – Garrett

    - Event Sharing – David

    - Integration of modules for MVP – Anna

  - Week 7

    - Priority integration into availability algorithm – David

    - Priority integration into DB – Stella

    - Display Available Times in UI/UX during “Event Finalization” – Garrett & Anna

    - Convert algorithm output from raw list to visual display – Anna & Garrett

  - Week 8

    - Milestone: Progress Meeting 3 – All Members

    - Unit Testing of Availability Algorithm (ensure edge cases present) – David

    - Integration Testing (Ensure Google Sync doesn’t crash DB) – Anna

    - Security and Structure Audit of DB (verify token encryption and 3NF) – Stella

    - Usibility Testing (Verify UI is functional for homepage and event finalization) – Garrett

  - Week 9

    - Finalize Priority Ranking System Algorithm – All Members

    - Integrate Priority System into Search Algorithm for Availability – David & Anna

    - Ensure real time functionality with multiple participants – Anna & Garrett

  - Week 10

    - System Review (Finalize Source Code) – All members

    - Final Submission (Report/Presentation/Video) – Garrett

- Monitoring and reporting:

  - We will be learning (attempting) to track team member contributions using the Jira Software for use during our Weekly Tuesday Sprint Retrospectives.

  - We will verify individual contributions by complying with modern Git commit and branching protocals for software engineering projects of this size. The use of commit frequency and lines added/removed creates an accountability system that is useful during the project and a quantifiable metric for the graders.

  - Progress will be tracked using existing tools (Jira and GitHub), with updates reviewed during weekly sprint meetings (number of commits + lines added/removed).

    - Given team size this data will not live as a formal document, but this data is available upon request and will be formatted upon final submission according to the official git logs.

- Building plan:

- User authentication and login credentials – <1 week

  - Dependency: None (Starting point of development)

- Establish server-client communication – <1 week

  - Dependency: None (Infrastructure)

- Working homepage – <1 week

  - Dependency: Server-client communication

- Retrieve and Display Google Calendar – <1 week

  - Dependency: User accounts and login credentials

- Design and Implement Database and how to Store Event Data – 1.5 weeks

  - Dependency: Retrieve and Display Google Calendar (must know data structure)

- Develop Availability algorithm – <1 week

  - Dependency:

    - Mock data,

    - OR database implementation

- Share events with others – <1 week

  - Dependency: Database implementation & Security

- Petition/Query the system for Availability – <1 week

  - Dependency: Search Algorithm

- Implement Priority System (Backend/Functionless) – <1 week

  - Dependency: Database Implementation

- Integrate Priority System into Search Algorithm – 1 Week

  - Dependency: Priority system & Search algorithm

- Records and Artifacts:

  - Product Backlog (Google Docs)

  - Sprint Backlog (Google Docs)

  - Requirement tracking and assignment/completion dates (Jira)

  - Running agenda / meeting minutes (Google Docs)

  - Change to structure/architecture log: (Google Doc)

  - MVP Increment (GitHub Repository)

  - AI Use Document (Google Docs).

- Rationale:

  - We broke the project into these steps based on our discussions and implementation of the spiral method of development.

  - We are viewing our development through the lens of users and building functionality based on how users will be using the app. Thus, the steps are progressive from logging in to connecting a calendar to finding availability to etc....

  - Each core development step was purposefully broken down into chunks that fit our scrum weekly cycle while still avoiding “reverse scheduling” or backwards risk/time assessments.

  - We chose to have daily standups to supplement our weekly sprint retrospectives to ensure that friction in the development process can be addressed and resolved quickly. The technical debt of limiting official team communications to once a week is far too great for the time constraints on the project.

- Risk Mitigation:

| Risk | Preventative Methods | Likelihood | Impact | Developer Responsible for Tracking Risk |
| --- | --- | --- | --- | --- |
| Google API rate limits | Reactive “Degraded” mode for server and computation. | Low | Medium (Requires Degraded server mode) | David & Stella |
| OAuth Complexity | Narrowing scope and server-side authentication tokens for reuse. | Medium | Low (UX) | Garrett |
| TIME CONSTRAINT (10 weeks) | MVP first, “fairness & extensions” later | High | High | Development Team |
| Data Persistence: “Mirroring” | Minimize storage of sensitive data per user (event information/titles) and ensure proper encryption before committing to storing any part of data | Medium | Medium | Anna & David |
| Scope Creep (Team attempts to instantiate two-way synchronization) | Read only policy on google calendar data and defensive synchronization strategies for conflicts. | Low | High | Stella |

Visual: Gannt Chart